## Backend Tasks
# | Priority | Area | Task | Why / Evidence | Depends on
1 | HIGH | Deploy | Redeploy staging with latest main (contains the ORA-00027 workaround) | The backend now clears DBMS_SESSION identifier + DBMS_APPLICATION_INFO action/module before every PL/SQL call, which neutralises the EBS "kill the user's SSHR sessions" loop that was killing our own pooled session (ORA-00027 on school-fees/leave-apply/dependents-update). Also carries person_id support on GET /leave/lov/amend, the composite leave formats, the school-fees composite child name and the dependents-delete code rule. Re-verify those three endpoints right after the deploy. | —
2 | HIGH | Verify | After the deploy: re-run dependents/update, leave/apply, school-fees AND letters/apply | The first three shared the ORA-00027 defect (session-label fix); letters/apply carries the new rules (valid name+language pair, no p_country). Use tools/resilient-runner.js with the phase cases, then regenerate the collection + reports. | Deploy
3 | MEDIUM | Tooling | Dev console now sends SQL base64-encoded (WAF workaround) | The F5/WAF in front of staging rejects any request body that looks like SQL, which silently broke the worksheet (HTML "Request Rejected" instead of JSON). /execute and /explain accept `sqlB64`; the page uses it automatically. Same trick is available to any internal tooling that must post SQL. | —
4 | MEDIUM | Timeout | School-fees submit exceeds the 30 s HTTP timeout while succeeding in Oracle | Verified: the client received 504 but the procedure committed with p_success_flag=Y. Either raise REQUEST_TIMEOUT_MS for submit routes, or return 202 + a way to confirm; mobile must not treat 504 as failure (duplicate submissions). | —
5 | HIGH | Environment | Set CERNER_BASE_URL (+ CERNER_TIMEOUT_MS) on staging | All 4 appointments endpoints return 503; code path is ready (expected shapes documented). Coordinate with DevOps. | DevOps
6 | HIGH | Feature gap | Expose an endpoint listing the caller's dependents (dependent_id + names) | Mobile cannot call dependents/update or /delete without ids; profile only surfaces dependents that own phones/addresses (empty for test user). Needs DB team to confirm the right view. | DB team
7 | HIGH | Follow-up | Chase the DB-team blockers report (9 items) and retest after each fix | Blockers file: reports/HMC-Sanaad-DB-Team-Report.xlsx. Re-run the Postman collection / tools scripts to refresh captured examples after fixes. | DB team
8 | MEDIUM | Feature gap | Return objectVersionNumber with profile phones[] | Phone UPDATE path binds p_object_version_number, but GET /profile does not expose it — mobile cannot do optimistic-locking updates once the phone-type defect is fixed. | DB Blocker #1
9 | MEDIUM | Performance | Warm-up / cache strategy for slow first-call views | WORKLISTS_V, RFMI_USER_LOV, LEAVE_AMEND_V, leave defaults/request-lov take 15-30 s on cold cache (real 504 captured). Options: startup warm-up queries, longer LOV cache TTL, or DB-side tuning (also raised with DB team). | DB team (partly)
10 | MEDIUM | API design | GET /leave/lov/request-lov requires enum but never uses it | Controller validates ProfileQueryDto (enum required) yet service.requestLov(q.lang) ignores it — either scope the read by user or drop the required param. | —
11 | MEDIUM | Docs/product | Decide op 66 (annual-ticket master) contract | Spec maps op 66 to TICKET_MASTER keyed by person_id (rich contract-year + contacts rows); backend intentionally serves user-scoped ANNUAL_TICKT_LOV (TICKET_MASTER unfiltered timed out). Confirm with product/mobile which shape the app needs. | Product
12 | MEDIUM | Auth | Configure USERS_DB_* on staging + verify the real auth cycle (SMS OTP, MPIN persistence) | PR #8 merged and DEPLOYED — GET /health/users-db (new) reports "Users DB host/database/user missing — pool not initialized". Once configured, capture real 401/403 + OTP examples and update the collection (auth folder currently reflects dev bypass). | Env config
13 | MEDIUM | Deploy | Payslip count new response shape not live yet | Commit 0616ca8 changes GET /payslip/count to { count, rows[{PERIOD_NAME, PERIOD_NAME_AR, ASSIGNMENT_ACTION_ID}] } (feeds op 11), but staging still returns { count } — include in next deploy and re-capture the Postman example. | Deploy
14 | LOW | Infra | Investigate intermittent F5/WAF "Request Rejected" HTML on some POSTs | Captured twice (support IDs 15468526370044169128 / 15468526370046194779 / 15468526370053122202). The WAF returns 200 with an HTML body — mobile JSON parsers will choke; ask infra which rule triggers. | Infra/WAF
15 | LOW | Gateway | Gateway /docs only documents the auth journey | Proxied business routes are invisible in the public swagger; consider serving the backend swagger (or a filtered copy) through the gateway for partners. | —
16 | LOW | Tooling | Keep tools/ scripts as the regeneration source | update-collection.js + update-collection-2.js + results-phase*.json rebuild the entire verified Postman collection on top of any baseline; verify-collection.js + compare-swagger-postman*.js guard drift. | —