## Summary
Report | HMC Sanaad B2E — Database Blockers Report (Staging)
Date | 2026-08-23
Environment | Staging — https://sndstgmobileapi.hamad.qa (gateway) → HMC_BackEnd → Oracle EBS (APPS schema)
Scope | All business modules (auth journey excluded per agreement). Every endpoint was exercised live against staging; requests below use ONLY values sourced from the system's own LOVs / views.
How errors were captured | GET /api/v1/diagnostics/oracle-logs on staging records every Oracle call with SQL, binds, duration and the full ORA error / OUT parameters.
Re-check (2026-08-23 PM) | All blockers re-tested after the latest deploy: the ORA-00027 kill-session defects in LEAV_OF_ABSEN_NEW_PR and ADD_DEPENDENT_PKG were fixed at the time. The remaining items were re-verified and still failed identically.
Re-check (2026-08-24, after your answers + our new SQL console) | Your answers unlocked LEAVE AMEND + CANCEL (composite "Leave Type¦start¦end") and gave us the dependent ids — thank you. We then stood up an internal SQL console, read the procedure sources and package specs directly, and closed SIX items from our side: SCHOOL FEES (p_child_name must be the child-view composite "Name¦¦Gender¦¦DD-MON-YY"), DEPENDENTS DELETE (relationship must be the CODE), DEPENDENTS UPDATE (relationship must be the MEANING + sponsorship from HMC_HR_SPONSORSHIP_PERSON + full flexfield), LETTERS (letter/language must be a valid pair and p_country only applies to the Saudi passage letter), PHONE UPSERT (the parameters are PL/SQL COLLECTIONS — we were binding scalars, which is why every phone type was "rejected"), and the ORA-00027 family (root cause in item #3, worked around in our build). What is still genuinely yours is listed below: mainly the ORA-00027 loop itself, the missing CREATE-phone entry point, the ORA-06502 buffer, FND_SESSIONS, the payslip cursor, and the remaining test data.
Key | Sheet "DB Blockers" = procedure/data defects blocking a success path. Sheet "Test Data Needed" = staging data we need seeded. Sheet "Verified OK" = procedures already returning successflag S (for contrast/scope).

## DB Blockers
# | Severity | Module / API | Oracle Object | Error (exact) | Request We Send (proven-correct format) | DB Reply | Evidence / Repro | WHAT WE NEED FROM DB TEAM | Status
1 | HIGH | Contact — POST /contact/phone (op 28: add/update phone) | XXHMC_SND_PHONE_PKG.ADD_OR_UPDATE_PHONE | p_success_flag = N — "Phone type doesnot exist" for EVERY phone type value | BEGIN XXHMC_SND_PHONE_PKG.ADD_OR_UPDATE_PHONE( p_user_name => 'AIBRAHIM39', p_phone_id => NULL, p_object_version_number => NULL, p_phone_type => 'Qatar Mobile Number', p_phone_number => '55512345', p_success_flag => :out, p_error_msg => :out, p_error_msg_ar => :out); END; | {"p_success_flag":"N","p_error_msg":"Phone type doesnot exist","p_error_msg_ar":"نوع الهاتف غير موجود"} | CAUSE FOUND ON OUR SIDE 2026-08-24 — the phone type was never the problem. The package spec declares TYPE ETSND_VARCHAR IS TABLE OF NVARCHAR2(4000) INDEX BY PLS_INTEGER, and p_phone_id / p_object_version_number / p_phone_type / p_phone_number are all COLLECTIONS of that type. We were binding scalars, so the collection arrived EMPTY and the package answered "Phone type doesnot exist". Using the package's own str_to_type() (comma-separated → collection, verified str_to_type('a,b').COUNT = 2) the call returns p_success_flag = Y. | Two things now: (1) NOTHING to fix for the type validation — closing that part. (2) THERE IS NO WAY TO ADD A PHONE: despite the name, ADD_OR_UPDATE_PHONE requires an existing p_phone_id (id 0 → "Phone ID doesnot exist", empty element → ORA-01403), and str_to_type() DROPS empty tokens (str_to_type('310129,').COUNT = 1), so a new-phone slot cannot be expressed at all. Please confirm the intended entry point for CREATING a phone, or make str_to_type preserve empty elements. (3) Minor: the procedure commits internally even when the caller aborts — worth knowing. | RESOLVED (update path)
2 | MEDIUM | School Fees — POST /school-fees/apply (op 39) | APPS.XXHMC_SND_SCHOOL_FEE_PR | WAS ORA-01403 @ line 197 — SOLVED on our side 2026-08-24 (successflag Y). Only the shared kill-session defect (line 114, item #3) still hits it intermittently. | The ORA-01403 was OUR payload, not your data: line 197 resolves the child with SELECT child_id INTO … FROM TABLE(xxhmc_snd_child_dets_view(<acd_st_dt>, <user>)) WHERE dob = p_child_name; so p_child_name must be the view's COMPOSITE "DOB" value (Name¦¦Gender¦¦DD-MON-YY), e.g. "Jerome Amir Sami Samir Ibrahim¦¦Male¦¦23-SEP-10" — not the plain name. With that value the whole procedure completed: p_success_flag = Y. | {"p_success_flag":"Y","p_error_msg":null} | Found by reading the procedure source through the new internal SQL console; verified live on 2026-08-24 (Oracle log 06:13:36Z). | No fix needed for line 197 — closing it. TWO smaller asks: (a) the naming is very confusing (a column called DOB holding "name¦¦gender¦¦dob", and a parameter called p_child_name expecting it) — please consider exposing CHILD_ID directly; (b) the submit takes >30 s, longer than our HTTP timeout, so clients get a 504 for a request that actually succeeded — can the procedure be profiled? | RESOLVED
3 | HIGH | Leave — POST /leave/apply (op 10) | APPS.XXHMC_SND_LEAV_OF_ABSEN_NEW_PR | WAS: ORA-00027 @ line 168 — FIXED (verified 2026-08-23 PM) | p_user_name=AIBRAHIM39, p_absence_type=Casual Leave (op 12 LOV), p_start_date=2026-09-07, p_end_date=2026-09-07 | NOW returns proper business rules: N "Leave Days cannot be applied more than 1 days for HMC Law employees" (for >1 day) and N "To avail this function, please submit the Policy Awareness questionnaire." | Re-verified after the fix — the procedure works; only the Policy-Awareness prerequisite blocks a successflag S for the test user (moved to Test Data Needed #7). | Nothing further on the procedure — RESOLVED. See Test Data Needed #7 (submit/waive the Policy Awareness questionnaire for the test user). | RESOLVED
4 | MEDIUM | Leave — POST /leave/return (op 56) — format mismatch LOV vs procedure | APPS.XXHMC_SND_RET_FRM_LEAV_PR + XXHMC_SND_RFL_LEAVE_DET_LOV (op 55) | ORA-06502 @ line 196 when the LOV's LONG display string is sent; the SHORT composite works (2026-08-24) | CONFIRMED FROM THE SOURCE: line 60 declares `lc_segment5 VARCHAR2(60)` and line 196 does `lc_segment5 := p_leave_details;`. The op 55 LOV returns a 75-character display string ("Casual Leave¦Leave Start Date : 19-APR-2026 and Leave End Date : 19-APR-2026") → overflows → ORA-06502. The 36-character short composite ("Casual Leave¦19-APR-2026¦19-APR-2026") fits and resolves correctly. | Short format: {"p_success_flag":"N","p_error_msg":"To avail this function, please submit the Policy Awareness questionnaire."} — i.e. the lookup succeeded; only the questionnaire prerequisite remains. | Both formats tested back-to-back on 2026-08-24; declaration + assignment read directly from ALL_SOURCE. | Either widen `lc_segment5` (line 60) to at least VARCHAR2(120), or change the op 55 LOV (RFL_LEAVE_DET_LOV) to return the short composite the procedure can actually hold. Right now the LOV and its consumer disagree by design. | OPEN
5 | LOW | Letters — POST /letters/apply (op 17) | APPS.XXHMC_SND_HR_EMPLYMNT_LTR_PR | WAS ORA-01403 @ lines 180 / 201 — EXPLAINED from the source 2026-08-24; both were OUR payload, not your data | Line 180 pairs the letter with a language: … flex_value_meaning = p_letter_name AND UPPER(NVL(ffv.description,'xyz')) = UPPER(p_letter_language) and each letter exists in exactly ONE language (Basic Salary Certificate = Arabic, Bank letter = English), so our English+Arabic-letter combination could never match. Line 201 (country) is guarded by: AND 'Passage to Saudi Arabia' = lc_segment3 -- the letter itself so sending p_country with any other letter can never match either. We now omit it. | ORA-01403 at 180 (wrong name/language pair) or 201 (country sent with a non-Saudi-passage letter) | Read from ALL_SOURCE through the internal console; the letter/language pairing is visible in XXHMC_SND_LETTER_NAME_LOV (FLEX_VALUE_MEANING + DESCRIPTION). | No data fix needed — we corrected our payload (p_country is now optional, and clients must use the language that belongs to the chosen letter). ONE small ask: expose the letter↔language pairing in the op 16 service response explicitly, and consider raising a business message instead of letting NO_DATA_FOUND escape as a raw ORA-01403. | RESOLVED
6 | LOW | Dependents — POST /dependents/update (op 24) | APPS.XXHMC_SND_ADD_DEPENDENT_PKG.XXHMC_SND_UPDATE_DEPENDENT_PR | WAS ORA-00027 @ line 3506 then ORA-01407 / ORA-20001 — ALL RESOLVED 2026-08-24 (successflag Y with your id 329302) | Thanks for the ids. After the kill-session workaround (item #3) the procedure walked us through its real requirements: 1. p_relation_ship needs the MEANING here ('Child'); a code ('C') or NULL → ORA-01407 CONTACT_TYPE to NULL. NOTE: op 31 REMOVE_DEPENDENT wants the CODE for the same concept — the two procedures disagree. 2. p_type_of_sponsership must exist in HMC_HR_SPONSORSHIP_PERSON — 'Employee' passes, 'Father' → ORA-20001 FLEX-VALUE DOES NOT EXIST. 3. The whole dependent flexfield is re-validated, so passport + QID + visa numbers/dates and p_visa_validy are all required even for a one-field change. | {"p_success_flag":"Y","p_error_msg":null} | Verified live 2026-08-24 after the session-label workaround; each rule was isolated one error at a time. | Nothing blocking — closing. Two consistency asks: (a) align the relationship parameter between UPDATE (meaning) and REMOVE (code); (b) stop concatenating raw ORA text into p_error_msg ("Dependent doesnot exitsORA-01403…"). | RESOLVED
7 | HIGH | SYSTEMIC ROOT CAUSE — every ORA-00027 across the submit procedures | XXHMC_SND_SCHOOL_FEE_PR (114) · XXHMC_SND_LEAV_OF_ABSEN_NEW_PR (168) · XXHMC_SND_ADD_DEPENDENT_PKG (3506) — same copy-pasted block | ORA-00027: cannot kill current session (intermittent, looked random) | Every one of those procedures starts with: FOR r IN (SELECT s.sid, s.serial# FROM v$session s WHERE client_identifier = p_user_name AND action IN ('PER/XX_HMC_SSHR_EMP_SELF_SERVICE', 'XX_HMC_SSHR_EMP_SELF_SERVICE_Q', 'XX_HMC_SSHR_EMP_SPECIAL', 'XX_HMC_SSHR_EMP_SELF_SERVICE_R')) LOOP EXECUTE IMMEDIATE 'ALTER SYSTEM KILL SESSION …'; END LOOP; | PROOF (v$session on staging): our own backend connection — SID 4820 ¦ CLIENT_IDENTIFIER = AIBRAHIM39 ¦ ACTION = PER/XX_HMC_SSHR_EMP_SELF_SERVICE ¦ PROGRAM = node@9ad3e43d28d1 A previous procedure on that POOLED connection ran fnd_global.apps_initialize, which stamps exactly those labels on our session — so the loop matches ITSELF and Oracle refuses: ORA-00027. | Explains the "random" behaviour perfectly: it depends on whether the pooled connection you land on was already used for an EBS procedure. Also explains why the same call fails then succeeds on retry. | WORKAROUND ALREADY SHIPPED ON OUR SIDE (build 2026-08-24+): we clear DBMS_SESSION identifier + DBMS_APPLICATION_INFO action/module before every PL/SQL call, so the loop can no longer match us. STILL PLEASE FIX PROPERLY: the loop should exclude the current session (AND s.sid <> SYS_CONTEXT('USERENV','SID')) — otherwise any pooled/EBS caller keeps hitting it. Also reconsider whether an integration API should be killing user sessions at all. | OPEN
8 | MEDIUM | SYSTEMIC — several submit procedures | APPLSYS.FND_SESSIONS (constraint FND_SESSIONS_U1) | ORA-00001: unique constraint (APPLSYS.FND_SESSIONS_U1) violated — intermittent | Observed on XXHMC_SND_SUPERVISOR_PR (line 95) and XXHMC_SND_HR_EMPLYMNT_LTR_PR (line 97) when calls run in quick succession over the backend's pooled connections. | ORA-00001: unique constraint (APPLSYS.FND_SESSIONS_U1) violated — ORA-06512: at "APPS.XXHMC_SND_SUPERVISOR_PR", line 95 | Same request succeeds on retry — the FND session initialization inside the procedures collides when the same pooled Oracle session initializes twice. | Review the fnd_global / FND session initialization at the top of the XXHMC_SND_* submit procedures so it is idempotent per session (handle existing FND_SESSIONS row instead of inserting blindly). This also likely explains the ORA-00027 family (items 2, 3, 6). | OPEN
9 | MEDIUM | Payslip — GET /payslip (op 11) | APPS.XXHMC_SND_PAYSLIP_PR | ORA-24338: statement handle not executed (NJS-107 invalid cursor) when the person/period has no payslip | p_person_id=852709, p_payperiod='January 2026', p_assignment_id=7179444713 | NJS-123/ORA-24338 — the earnings/deductions REF CURSORs are never OPENed on the no-data path. | person_id 26023 + January 2026 → full real payslip returned (WORKS). person_id 852709 + same period → ORA-24338. | Always OPEN the OUT REF CURSORs (even for zero rows) or raise a clean business error when no payslip exists for the period. | OPEN
10 | LOW | Dependents — POST /dependents/delete (op 31) | APPS.XXHMC_SND_REMOVE_DEPENDENT_PR | WAS ORA-20001 "Contact Type … does not exist" — SOLVED on our side 2026-08-24 (successflag Y, dependent 1607679) | Source line 253 forwards our parameter straight to the HR API: hr_contact_rel_api.update_contact_relationship(p_contact_type => p_relation_ship …) so it needs the CODE, not the meaning: p_relation_ship = 'C' succeeds, 'Child' raises ORA-20001, and omitting it raises ORA-01407 (CONTACT_TYPE → NULL). | {"p_success_flag":"Y","p_error_msg":null} | Verified live 2026-08-24 after reading the source through the internal SQL console. | Nothing blocking — closing. Optional: the parameter is named p_contact_type in the signature but the procedure ignores it and uses p_relation_ship instead (line 253); either use it or drop it, it is misleading. | RESOLVED
11 | MEDIUM | Performance — first (cold) call timeouts | XXHMC_SND_WORKLISTS_V · XXHMC_SND_LEAVE_AMEND_V · XXHMC_SND_RFMI_USER_LOV · leave defaults/request-lov views | ORA-03156 / gateway 504: first query on a cold cache exceeds the 25–30 s call timeout; warm calls take 1–3 s | e.g. SELECT * FROM XXHMC_SND_WORKLISTS_V WHERE (recipient_role = :u AND more_info_role IS NULL) OR more_info_role = :u | NJS-123: call timeout of 25000 ms exceeded → HTTP 500/504 on the first call only | Reproducible after every DB idle period: WORKLISTS_V 25 s → then 1.5 s; RFMI_USER_LOV 30 s → then 2.7 s. | Tune / add indexes for these views (they appear to full-scan WF tables on first execution), or provide materialized/pre-warmed versions. Mobile UX cannot absorb 25 s on first open. | OPEN

## Test Data Needed
# | Module / API | What is missing on staging | What we ask you to provide / seed | Blocking which test
1 | Annual Ticket — POST /annual-ticket/apply | PERSON_ID format confirmed by you (thanks) and re-tested — but person_id 26023 still has NO ticket entitlement: "No ticket balance available for Mr. Amir Sami Samir Ibrahim…" (re-verified 2026-08-24). | Seed a ticket balance/entitlement for person_id 26023 for contractual year 01-SEP-2025 to 31-AUG-2026, OR name a staging person_id who has one. | Success (successflag S) for op 67
2 | Approvals — POST /approvals/:id/decision | Still no OPEN actionable approval assigned to AIBRAHIM39 (worklist re-checked 2026-08-24: 49 rows, 0 actionable — only FYI/closed items; FYIs reject APPROVE). Signature + p_result=APPROVED/REJECTED confirmed working. | Have a test user whose supervisor is AIBRAHIM39 (e.g. VPAVITHRAN) submit a leave/HR request and leave it pending; send us its notification_id + item_key. | Success for op 22 approve/reject
3 | Leave — ops 57/58 amend & cancel | DONE ✔ — your composite format (Leave Type¦DD-MON-YYYY¦DD-MON-YYYY) + the 5 amendable leaves unlocked BOTH: amend and cancel now return successflag S (verified 2026-08-24). Nothing further needed. | No action — closed with thanks. | CLOSED — both verified S
4 | Dependents — ids for update/delete | Ids received ✔ (329302/329303/42465/1607679). Delete is now blocked ONLY on the contact-type value (see NEW Blocker #9); update is blocked on the regressed ORA-00027 (Blocker #6). | Answer Blocker #9 (exact p_contact_type value) and re-fix Blocker #6 — then both ops complete. | Success for ops 24 & 31
5 | Contact — POST /contact/phone/delete | Phone id 310129 confirmed by you, and the phone-type mystery is solved (it was our scalar binding, see Blocker #1). We still cannot create a DISPOSABLE phone to delete — ADD_OR_UPDATE_PHONE has no working insert path — and we will not delete the user's only real number. | Either give us a spare phone row we may delete, or tell us the intended CREATE-phone procedure so we can make our own. | Success for op 32
6 | Payslip — GET /payslip for arbitrary persons | Only some persons have payslips (26023 works; 852709 → ORA-24338). | Confirm which staging persons/periods have payslip data (or fix Blocker #8 so empty periods return cleanly). | Stable success for op 11
7 | Leave — POST /leave/apply + /leave/return | Both procedures now reach the same business prerequisite: "To avail this function, please submit the Policy Awareness questionnaire." (apply re-verified; return reaches it with the short composite format). Casual Leave is also limited to 1 day for HMC-Law employees. | Mark the Policy Awareness questionnaire as submitted for AIBRAHIM39 (or tell us which flow/user satisfies it), so ops 10 & 56 can return successflag S. | Success for ops 10 & 56

## Verified OK (context)
Oracle Object | API | Verified result (live, 2026-08-23)
XXHMC_SND_UPD_PERSONAL_INFO_PR | POST /profile/personal | successflag S
XXHMC_SND_SUPERVISOR_PR | POST /employee/supervisor | successflag S — p_new_supervisor must be the PERSON_ID from XXHMC_SND_SUPERVISOR_V (employee number fails the "HMC Change Supervisor" flexfield)
XXHMC_SND_QID_CHG_PR | POST /identity/qid/update | successflag S (yyyy-MM-dd dates accepted)
XXHMC_SND_COID_REQ_PR | POST /identity/idcard/apply | successflag S with op 59/60/53b LOV values
XXHMC_SND_CREATE_ADDRESS_PR | POST /contact/address | successflag S (country NAME; overlap rule enforced)
XXHMC_SND_UPD_ADDRESS_PR | POST /contact/address/update | successflag S (own address id + matching type + country NAME; date-track blocks same-date repeats)
XXHMC_SND_ADD_DEPENDENT_PKG.XXHMC_SND_ADD_DEPENDENT_PR | POST /dependents | successflag S once ALL flexfield-required segments are sent (attachment, passport no + expiry, country of issue, visa type, visa validity Yes/No, unique QID)
XXHMC_SND_PASS_DTL_PR | POST /dependents/passport/apply | successflag S
XXHMC_SND_HR_LEAV_AMEND_PR | POST /leave/amend | successflag S (2026-08-24) — composite p_leave_to_amend "Annual Leave¦12-MAR-2026¦12-MAR-2026" → new end 2026-03-13
XXHMC_SND_HR_LEAV_CANCEL_PR | POST /leave/cancel | successflag S (2026-08-24) — composite p_leave_to_cancel "Annual Leave¦12-MAR-2026¦12-MAR-2026"
XXHMC_SND_REASSIGN_PR | POST /approvals/:id/reassign | successflag S (DELEGATE of an own open notification)
XXHMC_SND_HR_RFMI_PR | POST /approvals/:id/request-info | successflag S (QUESTION on an own open item)
XXHMC_SND_TICKET_REQ_PR | POST /annual-ticket/apply | Format proven correct (PERSON_ID + SEP–AUG contractual year) — only the balance is missing (see Test Data #1)
XXHMC_SND_PAYSLIP_PR | GET /payslip | Real payslip returned for person_id 26023 / January 2026
XXHMC_SND_LEAVE_BALANCE_PR / CHILD_DETS_VIEW / all LOV views | GET endpoints | All read endpoints return real data (see API Reference workbook)